## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
|  |  | Bug submission accepted empty input without validation | Sprint 1 | Faith Tanaka Terera | Functional | Added mandatory input validation before analysis | 2026-07-07 | Closed | Verified successfully
|  |  | Historical bug embeddings were not indexed correctly | Sprint 1 | Faith Tanaka Terera | Data | Regenerated embeddings and rebuilt ChromaDB index | 2026-07-08 | Closed | RAG retrieval working
|  |  | Triage confidence score inconsistent for similar bugs | Sprint 2 | Faith Tanaka Terera | Logic | Updated confidence scoring logic | 2026-07-15 | Closed | Results stabilized
|  |  | Stack trace parser failed to extract failure point | Sprint 2 | Faith Tanaka Terera | Parsing | Improved regex extraction patterns | 2026-07-16 | Closed | Tested with multiple logs
|  |  | Multi-agent execution order incorrect in orchestrator | Sprint 2 | Faith Tanaka Terera | Integration | Fixed orchestration workflow | 2026-07-17 | Closed | Agents execute sequentially
|  |  | Root Cause Agent did not display confidence and supporting evidence | Sprint 3 | Faith Tanaka Terera | Functional | Enhanced Root Cause Agent to return confidence and RAG evidence | 2026-07-22 | Closed | Milestone 3 requirement satisfied
|  |  | Similarity score calculation produced inconsistent percentages | Sprint 3 | Faith Tanaka Terera | Logic | Refined similarity score calculation | 2026-07-23 | Closed | Display now consistent
|  |  | Recommendation Agent was not using historical RAG context | Sprint 3 | Faith Tanaka Terera | Integration | Integrated historical resolution into recommendations | 2026-07-24 | Closed | Recommendations improved
|  |  | Similar Bugs dashboard lacked structured bug details | Sprint 3 | Faith Tanaka Terera | UI | Redesigned Similar Bugs interface with bug details and resolution | 2026-07-25 | Closed | Improved readability
|  |  | Download report generated plain text instead of professional report | Sprint 3 | Faith Tanaka Terera | Enhancement | Upgraded report generation to PDF (in progress) | 2026-07-28 | Open | To be completed before Milestone 3 closure
|  |  | Analytics dashboard showed limited trends with insufficient analysed data | Sprint 4 | Faith Tanaka Terera | Functional | Validated analytics using multiple analysed submissions | 2026-08-04 | Closed | Analytics validated successfully
|  |  | Unverified resolved bugs could be added to the knowledge base | Sprint 4 | Faith Tanaka Terera | Functional | Added verification before ChromaDB ingestion | 2026-08-06 | Closed | KB growth workflow validated
|  |  | Generic recommendations for permission and authentication failures | Sprint 4 | Faith Tanaka Terera | Functional | Added defect-specific root-cause and recommendation rules | 2026-08-08 | Closed | Recommendations improved
|  |  | E2E testing covered limited bug scenarios | Sprint 4 | Faith Tanaka Terera | Testing | Tested multiple exception and stack-trace formats | 2026-08-09 | Closed | Multiple scenarios passed
|  |  | Final outputs required consistency across dashboard and PDF report | Sprint 4 | Faith Tanaka Terera | Integration | Verified complete analysis-to-PDF workflow | 2026-08-10 | Closed | Final report validated

## Sheet2
Logical
User Interface
Maintainability
Standards
Others